## Migration Tracker
G&A Benefits Platform — Full Migration Effort Tracker
Ref: Master Benefits PRD — 6 Initiatives (A-F) · 5 Detailed PRDs (Foundation, New Business, Renewal, Copilot, Blueprint) · 22-Week Phased Delivery
# | Initiative | Feature / Work Item | Description | Priority | Status | Est. Days | Dependencies | Phase | Owner | Notes
FOUNDATION — Admin Console (F1-F10)
1 | A | Admin Console Shell | Top-level admin area with left-nav, role gating, tab navigation for all foundation modules | P0 — Critical Path | POC Done | 1 | Auth/RBAC | Phase 1 | FE | POC complete; prod needs SSO wiring only
2 | A | Connections Hub — PrismHR | PrismHR connector: auth, scheduled + on-demand sync, delta detection, field mapping, sync log | P0 — Critical Path | Partial | 5 | Prism API access | Phase 1 | BE | POC simulated; prod needs REST client + retry logic
3 | A | Connections Hub — ClientSpace | ClientSpace connector: case creation, approval routing, benefits page export | P1 — High | Partial | 3 | CS API access | Phase 1 | BE | Webhook integration + case object mapping
4 | A | Connections Hub — DocuSign | DocuSign connector: envelope creation, template mapping, signer routing, status callbacks | P1 — High | Partial | 2 | DocuSign API key | Phase 1 | BE | OAuth2 + envelope API — well-documented API
5 | A | Connections Hub — WorkSight | WorkSight/NextGen: enrollment portal data push, eligibility config | P2 — Medium | Design Only | 2 | WS API/import format | Phase 1 | BE | Needs SME call to confirm API mechanism
6 | A | Ongoing Sync — Stream 1 (Master Data) | Continuous sync of carrier rates, master plan catalog, plan-code crosswalks with versioning | P0 — Critical Path | Partial | 3 | F2 Prism connector | Phase 1 | BE | Diff-review, version history storage
7 | A | Ongoing Sync — Stream 2 (Client Records) | Client-master mirror + per-client on-demand refresh for renewal baseline | P0 — Critical Path | Partial | 3 | F2 Prism connector | Phase 1 | BE | Change-capture log, timestamps
8 | A | Master Plan Library | Browsable plan catalog synced from Prism: search, filter, rate tables by tier/year, rate-change diff | P0 — Critical Path | Partial | 3 | F2 Stream 1 | Phase 1 | FE+BE | POC has browse + metrics; swap to real data
9 | A | Pricing Stack | Buckets per carrier, admin-factor tables, commission schedules, risk-factor formula — versioned | P0 — Critical Path | Partial | 3 | None | Phase 1 | FE+BE | POC has calculator; add version mgmt + approver
10 | A | Parameters & Fees | ACA threshold (year-versioned), deduction options, fee schedule | P1 — High | Partial | 2 | None | Phase 1 | FE+BE | Straightforward CRUD + effective-dating
11 | A | Vocabularies | Managed dropdown lists: class types, waiting periods, entity types, etc. | P1 — High | Partial | 1 | None | Phase 1 | FE+BE | POC has class types; replicate for all lists
12 | A | Document Templates | Template editor with merge-field mapping: ER Confirmation, EE SRA (EN+ES), Booklet, Prism payload | P1 — High | Partial | 4 | Template engine | Phase 1 | FE+BE | Real template engine (WeasyPrint/Puppeteer)
13 | A | Validation Rules | Typed rule library: completeness, source-data, cross-field, audit gates — real-time evaluation | P0 — Critical Path | Partial | 3 | F3, F4 | Phase 1 | BE | POC has dynamic checks; productionize rule engine
14 | A | Roles & Access | Field-level perms (blue/yellow/green/red), role matrix, PHI/PII classification | P1 — High | Partial | 3 | Auth provider | Phase 1 | FE+BE | SSO claim mapping + field-level enforcement
15 | A | Underwriting Intake | Document upload + extraction config, field map, completeness check | P1 — High | Partial | 2 | AI extraction svc | Phase 1 | FE+BE+AI | Real extraction pipeline
NEW BUSINESS — CAP Build-out (NB1-NB9)
16 | A | Intake & Document Upload | Seed fields + document checklist + drag-drop multi-file upload with type detection | P0 — Critical Path | POC Done | 1 | None | Phase 1 | FE | Done; add S3 storage + virus scan
17 | A | AI Extraction & Completeness Gate | Extraction -> structured fields with confidence -> completeness gate before assembly | P0 — Critical Path | Partial | 5 | AI extraction svc | Phase 1 | BE+AI | POC static; prod needs extraction pipeline
18 | A | Pre-filled CAP Assembly | Fuse 3 sources with provenance, confirm buttons, Prism sync refresh icons | P0 — Critical Path | POC Done | 1 | F3, F4, F6, NB2 | Phase 1 | FE | POC fully interactive; add BE persistence
19 | A | Plan Design & Rates | Rate formula, contribution strategy, per-plan tier tables, ACA check | P0 — Critical Path | POC Done | 2 | F3, F4, F5 | Phase 1 | FE+BE | POC calculates live; add BE rate engine
20 | A | Readiness & Flagging | Dynamic validation, Fix/Dismiss, progress bar, handoff gate | P0 — Critical Path | POC Done | 2 | F8 | Phase 1 | FE+BE | POC dynamic; integrate with F8 engine
21 | A | Collaboration & Approval | Workflow lifecycle, per-field comments, @mentions, needs-you queue | P1 — High | Partial | 4 | F9, ClientSpace | Phase 1 | FE+BE | Workflow engine + notification system
22 | A | Booklet Generation & Versioning | Auto-generate booklet from F7 templates + CAP data, version, snapshot on sign-off | P1 — High | Partial | 3 | F7 template engine | Phase 1 | BE | PDF generation service
23 | A | Client Sign-off (DocuSign) | Route booklet via DocuSign, track status, advance lifecycle | P1 — High | POC Done | 2 | F2 DocuSign | Phase 1 | BE | POC state machine done; wire to real API
24 | A | Ben Admin Handoff & Prism Write-back | Structured payload, Ben Admin review, Prism API write-back, ClientSpace mirror | P0 — Critical Path | Partial | 5 | F2 Prism, CS | Phase 1 | BE | createBenefitPlanSetup integration
RENEWAL — CAP Renewal Flow (R1-R9)
25 | A | Renewal Radar / Book of Business | Queue of upcoming renewals from synced client records, urgency, owner, risk | P0 — Critical Path | POC Done | 1 | F2 Stream 2 | Phase 1 | FE | POC has 8-client queue; swap to real data
26 | A | Start Renewal & Pre-fill | Per-client refresh -> pre-fill from prior-year CAP + Prism + plan-code crosswalk | P0 — Critical Path | POC Done | 3 | F2 Stream 2, F3 | Phase 1 | FE+BE | Add real Prism refresh call
27 | A | Document Updates as Deltas | Upload -> extracted values as proposed deltas (accept/reject vs baseline) | P1 — High | POC Done | 2 | NB2 extraction | Phase 1 | FE+BE | Reuses NB2 extraction engine
28 | A | Data-Currency & Version Drift | Version comparison table, 'Bring Up to Date' with reviewable diff | P0 — Critical Path | POC Done | 2 | F2 drift detection | Phase 1 | FE+BE | POC has version table + rebase
29 | A | Renewal Diff & Review | Unified diff: client vs master changes, accept/flag, bulk approve | P0 — Critical Path | POC Done | 1 | R2, R4 | Phase 1 | FE | POC fully interactive
30 | A | Readiness & Approval | Dynamic readiness gates, Fix navigation, role-gated approve | P0 — Critical Path | POC Done | 2 | F8, F9 | Phase 1 | FE+BE | POC gates are dynamic
31 | A | Booklet & Annual Contract Mgmt | Booklet preview + generate, YoY sign-off history, route for signature | P1 — High | POC Done | 2 | F7, NB7 | Phase 1 | FE+BE | Shares booklet engine with NB7
32 | A | Client Sign-off | DocuSign routing, shared infrastructure with NB8 | P1 — High | POC Done | 1 | NB8 | Phase 1 | BE | Reuses NB8 flow
33 | A | Prism Write-back (Update) | Structured update payload + downstream checklist + Prism API update | P0 — Critical Path | POC Done | 4 | NB9 | Phase 1 | BE | Update operation needs plan-code migration
COPILOT — AI Assistant (CP1-CP7)
34 | A | Sidebar & Interaction Model | Persistent sidebar, system/user/agent messages, actionable cards | P0 — Critical Path | POC Done | 1 | None | Phase 1 | FE | POC complete
35 | A | Context Awareness & Grounding | Context assembly per turn: CAP ID, section, role, pinned versions | P1 — High | Partial | 3 | LLM orchestration | Phase 1 | BE+AI | Context window management
36 | A | Retrieve & Surface (Read Tools) | MCP-based read tools across CAP, Foundation, Prism, CS, DocuSign | P1 — High | Partial | 4 | MCP servers | Phase 1 | BE+AI | Wire to MCP tool-calling
37 | A | Act & Update (Write Tools) | Before->after preview, Apply/Discard, field edits, modeling | P1 — High | POC Done | 3 | CP3, MCP | Phase 1 | FE+BE+AI | POC has proposed changes; wire to real writes
38 | A | Explain & Reason | Rate math walkthrough, blocker explanation, YoY diff analysis | P1 — High | Partial | 2 | CP2, CP3 | Phase 1 | AI | LLM prompt engineering
39 | A | Suggested Actions / Proactive | Context-aware chips, proactive nudges | P2 — Medium | POC Done | 1 | CP2 | Phase 1 | FE+AI | Enhance with state-aware nudges
40 | A | Guardrails, Permissions & Audit | RBAC on copilot, PII minimization, synced-field refusal, audit | P0 — Critical Path | POC Done | 2 | F9, MCP | Phase 1 | BE | POC has guardrails; harden for prod
INFRASTRUCTURE & CROSS-CUTTING (Blueprint Tab 3, 7, 8)
41 | A | Database & Data Layer | PostgreSQL schema: Client, CAP, Product, Plan, PlanTier, UW, AdminConfig, TaxPlan, Document, AuditLog + Foundation entities | P0 — Critical Path | Not Started | 4 | None | Phase 1 | BE | Schema from ERD — straightforward migration from JSON
42 | A | Authentication & SSO | SAML SSO with G&A IdP, JWT sessions, role resolution | P0 — Critical Path | Not Started | 2 | G&A IdP access | Phase 1 | BE | Standard SAML integration
43 | A | API Layer (Backend) | Next.js API routes or FastAPI: CAP CRUD, Foundation CRUD, validation, rate calc, doc gen | P0 — Critical Path | Not Started | 8 | Database | Phase 1 | BE | Most logic exists in POC frontend; lift to API
44 | A | MCP Server — cap-data-mcp | 8 tools + 6 resources wrapping platform data (Blueprint Phase 1) | P1 — High | Design Only | 3 | API layer | Phase 1 | BE | Architecture defined; standard MCP SDK
45 | A | MCP Server — prismhr-mcp | 12 tools + 4 resources wrapping PrismHR APIs (Phase 2) | P1 — High | Design Only | 4 | Prism API access | Phase 1 | BE | Critical for Copilot + write-back
46 | A | MCP Server — CS/DocuSign/WS | Additional MCP servers for workflow, e-sign, enrollment (Phase 3-4) | P2 — Medium | Design Only | 3 | Respective APIs | Phase 1 | BE | Enables cross-system Copilot actions
47 | A | Audit Trail System | Field-change logging: who, when, what, old->new. SOX controls. | P0 — Critical Path | POC Done | 2 | Database | Phase 1 | BE | POC has real-time store; add DB persistence
48 | A | Versioning & Snapshot Engine | Effective-dating for G&A config, snapshot-on-finalize for signed CAPs | P0 — Critical Path | Not Started | 4 | Database | Phase 1 | BE | Version table pattern
49 | A | Notification & Alerting | In-app + email: renewal reminders, approval requests, SLA escalation | P2 — Medium | Not Started | 3 | Email service | Phase 1 | BE | Standard notification service
50 | A | Data Governance & PII | Field-level classification, encryption at rest + transit, HIPAA BAA | P1 — High | Design Only | 3 | Cloud provider | Phase 1 | DevOps | Blueprint Tab 7 classification scheme
51 | A | CI/CD & Cloud Deployment | Docker, staging + prod, automated testing, blue-green deploy | P0 — Critical Path | Not Started | 3 | Cloud account | Phase 1 | DevOps | Standard pipeline
52 | A | Reporting & Analytics | CAP metrics, renewal pipeline, throughput, contribution trends | P3 — Nice-to-have | Not Started | 2 | Database, API | Phase 1 | FE+BE | Post-launch enhancement
INITIATIVE B — AI Underwriting Assistant
53 | B | AI Document Extraction Engine | Core extraction pipeline: ingest PDFs, SBCs, carrier invoices; OCR + layout analysis; output structured plan data with field-level confidence scores | P0 — Critical Path | Not Started | 5 | Document storage, OCR service | Phase 2 | AI+BE | Handles 10,426 annual quotes; target 20-30 min savings per case
54 | B | SBC & Invoice Parser | Specialized parsers for Summary of Benefits & Coverage documents and carrier invoices; extract plan design fields, deductibles, copays, coinsurance, rate tiers | P0 — Critical Path | Not Started | 3 | B-53 Extraction Engine | Phase 2 | AI | SBC format is ACA-standardized; invoice formats vary by carrier
55 | B | Comparison Builder | Auto-populate underwriting comparison spreadsheet from extracted data; side-by-side carrier comparison with rate analysis and concession history | P0 — Critical Path | Not Started | 3 | B-54 SBC Parser | Phase 2 | FE+BE | Replaces manual 20-30 min scrubbing per quote
56 | B | Pre-Submission Completeness Gate | Validation engine that blocks incomplete submissions from entering the underwriting queue; actionable error messages listing missing fields | P1 — High | Not Started | 2 | B-53 Extraction Engine | Phase 2 | BE | 80-90% of submissions currently arrive incomplete
57 | B | Hero/Gradient Integration | Push extracted census + plan data to Hero/Gradient risk scoring platforms; pull risk scores back into comparison workflow | P1 — High | Not Started | 2 | B-55 Comparison Builder, Hero/Gradient API | Phase 2 | BE | Existing external platforms; API integration required
58 | B | Extraction Confidence Scoring & Review UI | Dashboard showing extraction confidence per field; human review queue for low-confidence fields; bulk approve for high-confidence extractions | P1 — High | Not Started | 2 | B-53 Extraction Engine | Phase 2 | FE+AI | Specialist reviews and confirms; system never auto-commits
59 | B | Age-Banded Rate Calculator | Automated age-banded rate calculation for large group quotes; tier mapping and composite rate derivation from extracted census data | P2 — Medium | Not Started | 1 | B-54 SBC Parser, F4 Pricing Stack | Phase 2 | BE | Large group quotes currently extend scrubbing time significantly
INITIATIVE C — Carrier Portal Automation
60 | C | Carrier Portal Inventory & Mapping | Comprehensive inventory of all open-market carrier portals; field mapping from Prism enrollment data to each carrier's portal fields; API vs RPA classification per carrier | P0 — Critical Path | Not Started | 2 | Carrier portal access | Phase 2 | BA+BE | Classification determines API vs RPA approach per carrier
61 | C | API Integration — Master Carriers | Direct API integration for carriers with published APIs (e.g., Guardian); Prism-to-carrier enrollment data push with confirmation capture | P0 — Critical Path | Not Started | 5 | C-60 Portal Inventory, Carrier API access | Phase 2 | BE | Start with highest-volume carriers; API preferred over RPA
62 | C | RPA Framework for Non-API Portals | Browser automation framework for carrier portals without API; form-fill from Prism data, screenshot capture, error handling | P1 — High | Not Started | 4 | C-60 Portal Inventory | Phase 2 | BE+DevOps | Eliminates 13-17 min manual entry per enrollment
63 | C | Enrollment Data Mapping from Prism | Standardized data extraction from Prism enrollment records; transform and validate against carrier-specific field requirements before submission | P0 — Critical Path | Not Started | 3 | F2 PrismHR Connector | Phase 2 | BE | Prism read integration already built in Phase 1
64 | C | Automated Enrollment Audit & Reconciliation | Post-enrollment verification: compare submitted data against carrier confirmation; flag discrepancies; maintain compliance audit trail in ClientSpace | P1 — High | Not Started | 2 | C-61/C-62 Carrier Integration | Phase 2 | BE | SOX-adjacent — coverage gap risk requires audit step
65 | C | Exception Routing & Specialist Review | Route enrollment exceptions to assigned Benefits Specialist with field-level context; specialist retains audit review authority | P1 — High | Not Started | 2 | C-64 Audit, ClientSpace | Phase 2 | FE+BE | Specialist audit review step always retained per PRD
INITIATIVE D — Service Automation (Ciklum Expansion)
66 | D | Automated Case Creation from Intake | Integration with Ciklum to auto-create ClientSpace cases from intake channels (phone, email, portal); eliminate manual triage logging | P1 — High | Not Started | 3 | Ciklum platform, ClientSpace API | Phase 3 | BE | Benefits Specialists spend 35% of time on WSE/client issue resolution
67 | D | Self-Service Routing for ID Cards & FAQs | Ciklum self-service layer routes low-complexity inquiries (ID cards, coverage verification) to carrier apps with guided prompts; complex cases to Specialist | P1 — High | Not Started | 3 | Ciklum platform, Carrier apps | Phase 3 | BE+FE | 2-6 ID card requests/day; 30-50 during peak OE
68 | D | AI After-Call Summarization | Auto-generate case notes from call transcripts; populate ClientSpace case records; flag follow-up actions | P2 — Medium | Not Started | 2 | Ciklum platform, ClientSpace API | Phase 3 | AI+BE | Eliminates manual post-call documentation
69 | D | ClientSpace Integration Layer | Bi-directional sync between Ciklum and ClientSpace for case status, assignment, and escalation; unified view across both platforms | P1 — High | Not Started | 2 | ClientSpace API, Ciklum API | Phase 3 | BE | Critical for maintaining single source of truth for case management
INITIATIVE E — Payroll Deduction Audit (Sidekick Expansion)
70 | E | Consolidated Prism Report Generation | Sidekick integration to auto-pull and merge 4+ Prism reports (deduction register, plan rates, prior period data) into single consolidated view | P0 — Critical Path | Not Started | 2 | Sidekick platform, Prism API | Phase 3 | BE | Currently 20-60 min/client pulling and combining reports manually
71 | E | CAP-to-Deduction Comparison Engine | Automated tier-by-tier comparison of Prism deductions against CAP rates; highlight mismatches with drill-down to employee level | P0 — Critical Path | Not Started | 2 | E-70 Consolidated Report, CAP Platform (Init A) | Phase 3 | BE | CAP Cloud Tool provides structured rate data as comparison baseline
72 | E | HSA Employer Match Auto-Calculation | Automated calculation of HSA employer match amounts from plan enrollment data and CAP specs; validate against Prism entries per employee | P1 — High | Not Started | 2 | E-71 Comparison Engine, CAP Platform | Phase 3 | BE | Currently entered manually per employee with no automated validation
73 | E | Exception-Based Variance Flagging | Surface only mismatched records for Specialist review; routine matches confirmed in bulk; exception routing to ClientSpace with variance detail | P1 — High | Not Started | 2 | E-71 Comparison Engine, ClientSpace | Phase 3 | FE+BE | Specialists review exceptions only; 23% of time currently on payroll reviews
INITIATIVE F — Benefits Reconciliation Tool Rollout
74 | F | Beacon UAT Completion | Complete user acceptance testing of Beacon reconciliation platform; document and resolve all blocking defects; validate employee-level invoice comparison accuracy | P0 — Critical Path | Not Started | 3 | Beacon platform access | Phase 3 | QA+BE | Beacon partially deployed but unreliable; Excel fallback currently required
75 | F | Production Stabilization & Monitoring | Production hardening: performance tuning, error handling, alerting dashboards; eliminate monthly Excel fallback dependency | P0 — Critical Path | Not Started | 2 | F-74 UAT Complete | Phase 3 | DevOps+BE | Recon Specialists spend 97% of time on reconciliation
76 | F | Payment Routing Automation | Automate carrier payment routing logic across 8 different payment methods; integrate with reconciliation output for exception-based payment approval | P1 — High | Not Started | 1 | F-75 Production Stable | Phase 3 | BE | 8 different carrier payment methods currently require manual routing

## Sprint Plan
Sprint Roadmap — 200 Total Person-Days · CAP Module: 2 Months (5 FTEs)
Phase 1: 140 days / 5 FTEs = 2 months · Phase 2: 36 days / 4 FTEs = 2 weeks · Phase 3: 24 days / 3 FTEs = 2 weeks
Sprint | Duration | Theme | Work Items (Ref #) | Team Focus | Key Deliverable | Dependencies / Risks
S1 | 2 wk | Foundation + Infra | #41 DB, #42 SSO, #43 API, #51 CI/CD, #1 Admin, #2 Prism, #6-7 Sync | 5 FTEs | DB, Auth, Prism sync, API deployed | Prism API account day 1
S2 | 2 wk | Foundation + Core Flows | #8-14 F3-F9, #16-20 NB1-5, #25-30 R1-6, #47-48 Audit+Ver, #34+40 CP1+7 | 5 FTEs | All F1-F10, NB+Renewal in DB | Heaviest — POC lifts directly
S3 | 2 wk | E-Sign + Copilot + MCP | #15 UW, #17 NB2, #21-23 NB6-8, #27 R3, #31-32 R7-8, #35-39 CP2-6, #44 MCP, #49 Notif | 5 FTEs | DocuSign, booklet, Copilot live | DocuSign API + template engine
S4 | 2 wk | Write-back + UAT | #24 NB9, #33 R9, #45-46 MCP, #5 WS, #52 Reports, E2E test, rate parallel-run | 5 FTEs | Prism write-back, UAT complete | Prism write perms needed
S5 | 2 wk | Init B+C (part 1) | #53-59 AI UW engine + extraction, #60-62 Carrier portal API+RPA | 4 FTEs | AI extraction + portal automation | AI service + carrier access
S6 | 1 wk | Init B+C (complete) | #63-65 Data mapping + audit + exceptions | 4 FTEs | Init B+C fully operational
S7 | 2 wk | Init D+E+F | #66-76 Ciklum + Sidekick + Beacon stabilization | 3 FTEs | Full benefits platform live | Vendor coordination
TOTAL | 22 weeks | Full G&A Benefits Platform | 76 work items across 6 initiatives | ~9 peak FTEs | Cloud CAP + AI UW + Carrier Automation + Service/Deduction/Recon platform expansions | Phased delivery reduces risk; each phase delivers standalone value

## Effort Summary
Full Platform Effort Summary — 6 Initiatives · 200 Total Person-Days
Category | Module Count | P0 Items | P1 Items | P2/P3 Items | POC Done | Partial | Not Started | Est. Prod Days | Est. FTEs (13 wks)
PHASE 1 — Init A: CAP Cloud Migration & Foundation (2 Months · 5 FTEs)
Init A: Foundation (F1-F10) | 15 | 6 | 7 | 2 | 1 | 12 | 2 | 40 | 1.0 FTE
Init A: New Business (NB1-NB9) | 9 | 5 | 4 | 0 | 5 | 3 | 1 | 25 | 0.6 FTE
Init A: Renewal (R1-R9) | 9 | 6 | 3 | 0 | 8 | 1 | 0 | 18 | 0.5 FTE
Init A: Copilot (CP1-CP7) | 7 | 2 | 4 | 1 | 3 | 3 | 1 | 16 | 0.4 FTE
Init A: Infrastructure | 12 | 5 | 3 | 4 | 1 | 0 | 8 | 41 | 1.0 FTE
Phase 1 Subtotal (Init A) | 52 | 24 | 21 | 7 | 18 | 19 | 12 | 140 | 5 FTEs × 2 months
PHASE 2 — Init B+C: AI Underwriting + Carrier Portal (3 Weeks)
Init B: AI Underwriting Assistant | 7 | 3 | 3 | 1 | 0 | 0 | 7 | 18 | 1.2 FTE
Init C: Carrier Portal Automation | 6 | 3 | 3 | 0 | 0 | 0 | 6 | 18 | 1.2 FTE
Phase 2 Subtotal (Init B+C) | 13 | 6 | 6 | 1 | 0 | 0 | 13 | 36 | 4 FTEs × 3 wks
PHASE 3 — Init D+E+F: Platform Expansions (2 Weeks)
Init D: Service Automation (Ciklum) | 4 | 0 | 3 | 1 | 0 | 0 | 4 | 10 | 1.0 FTE
Init E: Payroll Deduction Audit (Sidekick) | 4 | 2 | 2 | 0 | 0 | 0 | 4 | 8 | 0.8 FTE
Init F: Reconciliation Tool (Beacon) | 3 | 2 | 1 | 0 | 0 | 0 | 3 | 6 | 0.6 FTE
Phase 3 Subtotal (Init D+E+F) | 11 | 4 | 6 | 1 | 0 | 0 | 11 | 24 | 3 FTEs × 2 wks
GRAND TOTAL — ALL INITIATIVES | 76 | 34 | 33 | 9 | 18 | 19 | 36 | 200 | 5 FTEs peak · ~3 months
Key accelerators (Phase 1 — Initiative A):
1. Comprehensive POC serves as production scaffold — 80% of UI components lift directly with backend wiring
2. POC validated all business logic (rate formulas, validation rules, contribution strategies) — no re-discovery needed
3. MCP architecture standardizes all integrations — no custom wiring per feature
4. Dynamic validation, audit trail, and role system already proven in POC — prod adds persistence layer only
5. Renewal flow (R1-R9) has 8/9 modules POC Done — fastest path to value
Key accelerators (Phase 2 — Initiatives B+C):
1. Initiative A infrastructure (Prism connector, data layer, auth) reused directly — no duplicate integration work
2. Extraction pipeline architecture proven during Init A (NB2/F10) — scales to full underwriting scope
3. Carrier portal field mapping leverages Prism data layer built in Phase 1
Key accelerators (Phase 3 — Initiatives D+E+F):
1. Ciklum and Sidekick are vendor platform expansions — our scope is integration, not core platform build
2. Beacon UAT is testing and stabilization, not new development
3. ClientSpace integration pattern established in Phase 1 — reused for D, E, and F

## Risk Register
Full Platform Migration — Risk Register
# | Initiative | Risk | Impact | Likelihood | Severity | Mitigation | Owner
PHASE 1 RISKS — Initiative A: CAP Platform
1 | A | PrismHR API access not provisioned in time | High | Medium | High | Request in week 0. POC abstraction layer allows simulated data until live access arrives — zero blocking. | PM
2 | A | AI extraction accuracy below 90% confidence | Medium | Medium | Medium | Human-confirmation workflow (NB2/NB3) is built and proven. System augments, never auto-commits. | AI Lead
3 | A | HIPAA compliance gaps | High | Low | Medium | SOC 2 + BAA cloud. Field-level PII classification from Tab 7 already designed. Security review in S5. | DevOps
4 | A | AM adoption resistance (27 AMs) | High | High | Critical | Pilot with 5 AMs in S6. Copilot reduces learning curve dramatically. Side-by-side Excel comparison. | PM
5 | A | Rate calc discrepancy vs Excel | Critical | Medium | Critical | Parallel-run in S5: both systems compute rates for 10 clients, compare to $0.01. Formula proven in POC. | BE Lead
6 | A | Compressed timeline — quality risk | Medium | Medium | Medium | POC de-risks significantly: all UX validated, all business logic verified, all flows tested. Prod is wiring, not invention. | Tech Lead
7 | A | Open-market plans (no API/EDI) | Medium | High | High | Manual rate entry as primary path (matches current process). AI extraction as accelerator. | FE Lead
8 | A | Data migration from 100+ Excel CAPs | High | High | High | Build parser targeting Tab 1 structure. Batch import with validation. Keep Excel as read-only archive. | BE + Data
PHASE 2 RISKS — Initiatives B + C: AI Underwriting + Carrier Portal
9 | B | Document format variability across carriers | High | High | High | Start with ACA-standardized SBC format (consistent structure). Invoice parsers prioritized by carrier volume. Confidence scoring ensures low-confidence extractions route to human review. | AI Lead
10 | B | Extraction accuracy insufficient for production use | High | Medium | High | Human-in-the-loop design from day 1 — extraction is always review-and-confirm, never auto-commit. Confidence threshold tuned per field type. | AI Lead
11 | B | Hero/Gradient API access or compatibility issues | Medium | Medium | Medium | Hero/Gradient are existing platforms already in use. API documentation review in Sprint 7; fallback is manual entry into existing platforms. | BE Lead
12 | C | Carrier portal changes break RPA scripts | High | High | Critical | API integration preferred over RPA where possible. RPA scripts include visual validation and screenshot capture. Monitoring alerts on failure. Specialist manual fallback always available. | DevOps
13 | C | Carrier reluctance to provide API access | Medium | High | High | Start with carriers who have published APIs (e.g., Guardian). RPA as bridge for non-API carriers. Carrier relationship managed by G&A Benefits team. | PM
14 | C | Enrollment data mapping errors create coverage gaps | Critical | Medium | Critical | Dual-confirmation: automated enrollment verified against carrier confirmation response. Specialist audit review retained on every enrollment. SOX-compliant audit trail. | BE Lead
PHASE 3 RISKS — Initiatives D + E + F: Platform Expansions
15 | D | Ciklum vendor delivery timeline misalignment | Medium | Medium | Medium | Our scope is integration layer only — Ciklum owns platform expansion. Parallel workstreams with clear interface contracts. Fallback: current manual process continues. | PM
16 | D | Self-service deflection rate lower than expected | Medium | High | Medium | Phased rollout: start with ID card requests (highest volume, simplest routing). Measure deflection rate before expanding to other inquiry types. | BA
17 | E | Sidekick platform limitations for Prism integration | Medium | Medium | Medium | Sidekick is existing vendor with established Prism connectivity. Integration scope limited to consolidated report push and variance flagging. Fallback: current Prism report process. | BE Lead
18 | E | CAP rate data not structured for automated comparison | Low | Low | Low | Init A (Phase 1) delivers structured CAP data in the cloud platform — this is the primary enabler. Comparison engine reads directly from Init A data layer. | BE Lead
19 | F | Beacon UAT reveals fundamental platform defects | High | Medium | High | Scope is UAT completion and stabilization, not new development. If defects are severe, escalate to Beacon vendor. Excel fallback remains operational during stabilization. | QA Lead
20 | F | Recon Specialist resistance to Beacon adoption | Medium | Medium | Medium | Beacon is already partially deployed — team is familiar with the tool. UAT involves Recon Specialists directly. Excel fallback eliminated only after production stability confirmed. | PM

## Team & Resources
Team Composition — 200 Person-Days Total · CAP in 2 Months · Full Platform in ~3 Months
PHASE 1 — Initiative A: CAP Platform (Sprints 1-6, 12 Weeks) — 6 FTEs
Role | Count | Sprint Allocation | Key Responsibilities | Skills Required
Senior Frontend Engineer | 1 | S1-S4 (full) | React/Next.js components (lift from POC), Zustand-to-backend migration, Copilot UI, accessibility | React, TypeScript, Next.js App Router, inline styles, Zustand
Senior Backend Engineer | 2 | S1-S4 (full) | API design, PostgreSQL, PrismHR/CS/DocuSign integration, MCP servers, rate engine, validation engine | Python/Node.js, PostgreSQL, REST APIs, MCP SDK, PrismHR API
AI/ML Engineer | 1 | S2-S4 | Document extraction pipeline, LLM orchestration for Copilot, MCP tool-calling, prompt engineering | LLM APIs, document extraction, MCP SDK, prompt engineering
DevOps Engineer | 0 | (covered by BE) | CI/CD, Docker, cloud infra, monitoring, HIPAA compliance, staging/prod | AWS/Azure, Docker, Terraform, SOC 2 compliance
Product/Project Manager | 1 | S1-S4 (full) | Sprint planning, G&A stakeholder mgmt, SME coordination, UAT, change management | PEO/benefits domain, Agile delivery
Phase 1 Team Total | ~6 FTEs | 12 weeks | ~211 person-days of effort (Init A)
PHASE 2 — Initiatives B + C (Sprints 7-9, 6 Weeks) — Add 2 FTEs = 8 Total
Role | Count | Sprint Allocation | Key Responsibilities | Skills Required
Phase 1 team continues | 6 | S7-S9 (all continuing) | Core team from Phase 1 continues; BE engineers shift to carrier API integration; AI engineer shifts to extraction pipeline | Same as Phase 1
Senior AI Engineer (NEW) | 1 | S2-S4 | Production extraction pipeline: OCR, SBC parsing, invoice parsing, confidence scoring, age-banded rate handling | Document AI, OCR pipelines, ML model deployment, PDF processing
Integration/RPA Engineer (NEW) | 1 | S7-S9 | Carrier portal automation: API integration for supported carriers, RPA framework for non-API portals, enrollment data mapping | API integration, browser automation (Selenium/Playwright), Prism data model, carrier portal experience
Phase 2 Team Total | ~8 FTEs | 6 weeks | ~75 person-days of effort (Init B+C)
PHASE 3 — Initiatives D + E + F (Sprints 10-11, 4 Weeks) — Add 1 FTE = 9 Total
Role | Count | Sprint Allocation | Key Responsibilities | Skills Required
Phase 2 team continues | 8 | S10-S11 (all continuing) | Core team continues; AI/RPA engineers shift to Ciklum/Sidekick/Beacon integration and stabilization | Same as Phase 2
QA/Stabilization Engineer (NEW) | 1 | S10-S11 | Beacon UAT completion, production stabilization testing, cross-initiative regression testing, payment routing validation | QA automation, reconciliation domain, UAT methodology, production monitoring
Phase 3 Team Total | ~9 FTEs | 4 weeks | ~60 person-days of effort (Init D+E+F)
G&A-SIDE RESOURCES (Part-Time, All Phases)
Role | Count | Sprint Allocation | Key Responsibilities | Skills Required
Benefits SME (G&A) | 1 | S1-S6 (advisory, 50%) | Domain validation, rate formula verification, workflow confirmation, UAT | G&A CAP process, Prism knowledge
UW SME (G&A) | 1 | S7-S9 (advisory, 25%) | Underwriting workflow validation, extraction accuracy review, comparison template confirmation | G&A underwriting process, Hero/Gradient
Ben Admin SME (G&A) | 1 | S7-S11 (advisory, 25%) | Carrier enrollment validation, payroll deduction audit confirmation, Beacon UAT participation | Ben Admin processes, carrier portal experience
IT/Systems Contact (G&A) | 1 | S1-S11 (as needed) | Prism API provisioning, SSO configuration, carrier portal credentials, environment access | G&A IT systems, Prism admin
Why this lean team works across 22 weeks:
- POC eliminates discovery/design phase for Init A — team starts from validated, working code on day 1
- 18 of 52 Init A work items are already POC Done — these need backend wiring only, not UI development
- Phased delivery means team ramps gradually: 6 FTEs (Phase 1) -> 8 FTEs (Phase 2) -> 9 FTEs (Phase 3)
- Phase 1 infrastructure (Prism connector, data layer, auth, MCP) is directly reused by Phases 2 and 3
- Initiatives D, E, F are vendor platform expansions — our scope is integration, not core platform build
- Compressed 22-week timeline vs typical 40+ weeks for greenfield — POC de-risked all business logic for Init A

## Business Impact
Business Impact — G&A Beneficial Activity Baseline & Automation Yield
Source: Master Benefits PRD Tab 5 — Activity Baseline for G&A Beneficial (GAB) · 72 FTEs (62 onshore, 10 offshore)
GAB ACTIVITY BASELINE — % Time Allocation by Role
Process | AE-Existing (4) | AM-Existing (27) | AE-New (4) | AM-New (10) | Ben. Coordinator (5) | Ben. UW (1) | FTE Equiv. | Initiative
CAP Build-out & Completion | 10% | 10% | 20% | 20% | 10% | — | 6.4 | A
Benefits Booklet Preparation | 5% | 5% | 5% | 5% | 15% | — | 3 | A
Benefits Renewal | 30% | 35% | 5% | 5% | 10% | 2% | 11.9 | A
Sales Support & Prospecting | 5% | 5% | 10% | 10% | — | — | 3 | —
Client Requirements Gathering | 10% | 10% | 20% | 20% | 10% | 10% | 6.5 | —
Benefits Underwriting & Quoting | 5% | 5% | 10% | 10% | 30% | 75% | 5.2 | B
Enrollment Education | 10% | 10% | 10% | 10% | — | 5% | 4.6 | —
Welcome Packet Build | — | — | 5% | 5% | 10% | — | 1.2 | —
Broker Commission Verification | 5% | 5% | 5% | 5% | 10% | 1% | 2.8 | —
Strategic Client Outreach | 15% | 10% | 5% | 5% | — | 5% | 4.1 | —
QC & Work Audits | 5% | 5% | 5% | 5% | 5% | 2% | 2.5 | —
AUTOMATION YIELD PER INITIATIVE
Initiative | Target Process | Addressable FTEs | Automation Yield | Est. FTE Recovery | Key Metric | Baseline | Target | Source
A — CAP Migration | CAP Build-out & Completion | 6.4 FTE equiv. | 40-50% of CAP/Renewal labor | ~3-4 FTEs | Hours per CAP build | 2-4 hours | <30 min (review only) | PRD Tab 5
A — CAP Migration | Benefits Booklet Preparation | 3.0 FTE equiv. | 80-90% (auto-generated) | ~2.5 FTEs | Booklet prep time | Manual build | Auto-generated from CAP | PRD Tab 5
A — CAP Migration | Benefits Renewal | 11.9 FTE equiv. | 40-50% of renewal labor | ~5-6 FTEs | Renewal CAP time | Full manual rebuild | Pre-filled, review only | PRD Tab 5
A — CAP Migration | Ben Admin Setup (downstream) | ~4 FTEs (48% of Analyst time) | 20-30% rework eliminated | ~1-2 FTEs | Setup rework cycles | Frequent CAP errors | Validated CAP data | PRD Tab 4
B — AI UW Assistant | Benefits Underwriting & Quoting | 5.2 FTE equiv. (+ 20% UW capacity) | 60-70% of scrubbing time | ~3-4 FTEs | Min per quote scrub | 20-30 min | <5 min (review only) | PRD Tab 4
C — Carrier Portal | Open-Market Enrollment | ~20% of Specialist time | 80-90% of entry time | ~2-3 FTEs | Min per enrollment | 13-17 min | <2 min (audit only) | PRD Tab 4
D — Service Automation | WSE + Client Issue Resolution | ~35% of Specialist time | 30-40% deflection | ~4-5 FTEs | ID card req/day | 2-6 (30-50 peak) | Self-service | PRD Tab 4
E — Deduction Audit | Payroll Reviews & Deductions | ~23% of Specialist time | 70-80% of review time | ~3-4 FTEs | Min per client review | 20-60 min | Exception review only | PRD Tab 4
F — Reconciliation | Benefits Reconciliation | 5 FTEs (97% of Recon role) | 60-70% with stable Beacon | ~3-4 FTEs | Platform reliability | Partial (Excel fallback) | Full production | PRD Tab 4
TOTAL ADDRESSABLE IMPACT
Team | Total FTEs | Total FLC | Onshore / Offshore | Directly Addressable FTEs | Primary Initiatives
G&A Beneficial (GAB) | 72 FTEs | $8.2M | 62 onshore + 10 offshore | 31-32 FTEs | A (CAP), B (AI UW)
Benefits Administration | 98 FTEs | $7.1M | 68 onshore + 30 offshore | 12-16 FTEs | C (Portal), D (Service), E (Deduction), F (Recon)
COMBINED TOTAL | 170 FTEs | $15.3M | 130 onshore + 40 offshore | 43-48 FTEs addressable | All 6 Initiatives
Key assumptions:
- Init A addresses 21.3 FTE equiv. in GAB (CAP Build-out 6.4 + Booklet 3.0 + Renewal 11.9) + ~10 offshore FTEs + downstream Ben Admin Analyst impact
- Init B addresses 10,426 annual quotes at 20-30 min savings each = ~3,500-5,200 hours/year of scrubbing time recovered
- Init C addresses 13-17 min per open-market enrollment across all non-EDI carrier enrollments
- Initiatives D, E, F are vendor platform expansions with integration scope — impact projections from PRD Tab 4
- FTE recovery does not mean headcount reduction — freed capacity is redirected to strategic client outreach, complex case handling, and business growth